## Instructions
ANZ-Aligned Automation Productivity Tracker
10-day individual automation evaluation — ParaBank demo (https://parabank.parasoft.com/parabank/index.htm)
Legend
Yellow fill, blue text | Cells you (tester) or the evaluator type into. Safe to edit.
Light blue fill | Example row — shows the expected format. Do not delete; add new rows below it.
Black text, no fill | Formulas. Do not overwrite — they recalculate automatically.
How the workbook is organised
Daily Log | Fill in once per day (Day 1–10). Tracks planned vs completed cases, pass/fail counts, hours, flakiness, and blockers.
Test Case Tracker | One row per automated test case. Use the dropdowns for Module, Type, Priority, Complexity, Status and Result. Add rows as you go — validation is pre-applied to row 300.
Lists | Reference lists that power the dropdowns. Leave this sheet alone unless you want to add a new dropdown option.
Productivity Dashboard | Auto-calculated from the two sheets above. Nothing to type here — just read it.
Scorecard | Evaluator fills in a 1–5 rating per criterion at the end of Day 10. Weighted score and banding calculate automatically.
Application Coverage | Run-level results for ParaBank, ACME web profiles, and Android/Appium coverage. Only observed results are recorded; blocked and unrun suites are labeled separately.
Notes
• | This tracker measures volume AND quality together — a high case count with a low pass rate or high flakiness is not strong productivity.
• | The Test Case ID convention is TC-<Module abbreviation>-<3-digit number>, e.g. TC-TRF-001 for a Transfers test.
• | Update the Test Case Tracker as you build each script, not retrospectively — same-day logging gives more accurate velocity data.

## Lists (hidden)
Module | Test Type | Priority | Complexity | Automation Status | Execution Result | Y/N | Day
Framework | Positive | Critical | Low | Not Started | Pass | Y | 1
Registration | Negative | High | Medium | In Progress | Fail | N | 2
Authentication | Boundary | Medium | High | Automated | Not Run |  | 3
Accounts | Security | Low |  | Blocked | Skipped |  | 4
Transfers | Performance |  |  |  | Flaky |  | 5
Bill Payment | Regression | [5 empty] | 6
Transaction Search | [6 empty] | 7
Lending | [6 empty] | 8
API-REST | [6 empty] | 9
API-SOAP | [6 empty] | 10
Cross-Browser
Accessibility
Mocks-Extensions
ACME Web
ACME Mobile
Login & Authentication
Customer Registration
Open new Account
Accounts Overview & Balance
Fund Transfer
ParaBank Mobile

## Daily Log
Day | Date | Theme / Focus Area | Planned Cases | Completed Cases | Passed | Failed | Blocked | Completion % | Pass Rate % | Hours Spent | Flaky Tests Introduced | Flaky Tests Fixed | Defects Logged | Key Risk / Assumption Flagged | Blockers | Tester Notes
1 |  | Framework setup & smoke suite | 8 | 8 | 8 | 0 | 0 | 1 | 100% |  |  |  | 0 |  | None for isolated-target acceptance. | Grouped final headed acceptance results by planned scope day; original per-day dates and hours were not recorded.
200% |  | Registration & authentication depth | 1800% | 1800% | 1700% | 100% | 0% | 100% | 94.44% |  |  |  | 0% | Blank phone registration is accepted by ParaBank. | None for isolated-target acceptance. | Grouped acceptance: one expected application-gap failure.
300% |  | Accounts & balances | 1500% | 1500% | 1400% | 100% | 0% | 100% | 93.33% |  |  |  | 0% | ParaBank opens accounts from zero-balance sources. | None for isolated-target acceptance. | Grouped acceptance: one expected application-gap failure.
400% |  | Pay Anyone / fund transfers | 1800% | 1800% | 1200% | 600% | 0% | 100% | 66.67% |  |  |  | 0% | ParaBank accepts invalid amounts and same-account transfers. | None for isolated-target acceptance. | Grouped acceptance: six expected application-gap failures.
500% |  | BPAY-style bill payments | 1800% | 1800% | 1600% | 200% | 0% | 100% | 88.89% |  |  |  | 0% | Negative and overdrawn bill payments mutate account balance. | None for isolated-target acceptance. | Grouped acceptance: two expected application-gap failures.
600% |  | Transaction search & statement reconciliation | 1500% | 1500% | 1400% | 100% | 0% | 100% | 93.33% |  |  |  | 0% | Account activity is oldest-first, not newest-first. | None for isolated-target acceptance. | Grouped acceptance: one expected application-gap failure.
700% |  | Lending journey | 1500% | 1500% | 1500% | 0% | 0% | 100% | 100% |  |  |  | 0% |  | None for isolated-target acceptance. | All lending and flagship journey cases passed.
800% |  | REST/SOAP API layer | 2200% | 2200% | 2200% | 0% | 0% | 100% | 100% |  |  |  | 0% |  | None for isolated-target acceptance. | Independent REST/SOAP suite: 22/22 passed.
900% |  | Cross-browser, mobile, accessibility & PayID simulation | 1500% | 1500% | 1500% | 0% | 0% | 100% | 100% |  |  |  | 0% | Accessibility scans record violations; PayID paths are mocked. | None for isolated-target acceptance. | Headed Chromium, Firefox, and mobile each passed 15/15; Gherkin 4/4 scenarios, 29/29 steps.
1000% | 1000% | Current full-suite verification | 14400% | 14400% | 14300% | 100% | 0% | 100% | 99.31% |  | 0% | 0% | 100% | Current single-run verification showed 1 unexpected failure in bill payment negative amount handling. | None for isolated-target acceptance. | Latest run: 143 passed, 1 failed, 0 skipped, 0 flaky.
|  | TOTAL / ACCEPTANCE SUMMARY | 288 | 288 | 276 | 12 | 0 | 1 | 95.83% |  | 0 | 0 | 1 |  |  | Hours were not tracked. Three full reruns: 399 pass, 33 expected application-gap failures, zero unexpected failures, skips or flakes.

## Test Case Tracker
Test Case ID | Module | Scenario Description | Test Type | Priority | Complexity | Day Assigned | Day Completed | Automation Status | Execution Result | Reusable Component (Y/N) | Defect Raised (Y/N) | Defect ID / Link | Notes
TC-TRF-001 | Transfers | Transfer full available balance between own accounts; verify source hits zero and ledger entries match on both sides. | Boundary | High | Medium | 4 | 4 | Automated | Pass | Y | N |  | Example row — edit or delete before adding your own.
TC-AUT-001 | Authentication | Login page displays the username and password controls. | Smoke | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-AUT-002 | Authentication | API-seeded customer logs in and reaches account services. | Positive | High | Medium | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; API-seeded; Headed desktop acceptance 07/10/2026.
TC-AUT-003 | Authentication | Reject login with an unknown username. | Negative | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-AUT-004 | Authentication | Reject login with an incorrect password. | Negative | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-AUT-005 | Authentication | Reject login with a blank username. | Negative | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-AUT-006 | Authentication | Reject login with a blank password. | Negative | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-REG-001 | Registration | Registration form exposes all onboarding fields. | Smoke | High | Low | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; Headed desktop acceptance 07/10/2026.
TC-REG-002 | Registration | Register a new customer, confirm automatic sign-in, and verify the default account and balance. | E2E | High | Medium | 1 | 1 | Automated | Pass | Y | N |  | Smoke tagged; API/UI parity; Headed desktop acceptance 07/10/2026.
TC-REG-003 | Registration | Reject registration when first name is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-004 | Registration | Reject registration when last name is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-005 | Registration | Reject registration when street address is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-006 | Registration | Reject registration when city is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-007 | Registration | Reject registration when state is blank. | Negative | High | Low | 200% | 200% | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-008 | Registration | Reject registration when ZIP/postcode is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-009 | Registration | Reject registration when phone number is blank. | Negative | High | Low | 200% | 200% | Automated | Fail | Y | N |  | Expected application gap: ParaBank accepts registration with a blank phone number. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-REG-010 | Registration | Reject registration when SSN is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-011 | Registration | Reject registration when username is blank. | Negative | High | Low | 200% | 200% | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-012 | Registration | Reject registration when password is blank. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | Data-driven mandatory field; Headed desktop acceptance 07/10/2026.
TC-REG-013 | Registration | Reject a duplicate username. | Negative | High | Medium | 200% | 200% | Automated | Pass | Y | N |  | Uses API-seeded customer; Headed desktop acceptance 07/10/2026.
TC-REG-014 | Registration | Reject mismatched password and confirmation values. | Negative | High | Low | 2 | 2 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-REG-015 | Registration | Handle a 256-character first name without an application error. | Boundary | Medium | Medium | 200% | 200% | Automated | Pass | Y | N |  | Security payload probes are opt-in on shared demo; Headed desktop acceptance 07/10/2026.
TC-REG-016 | Registration | Handle special characters in first name without an application error. | Security | Medium | Medium | 2 | 2 | Automated | Pass | Y | N |  | Security payload probes are opt-in on shared demo; Headed desktop acceptance 07/10/2026.
TC-REG-017 | Registration | Handle SQL-injection-shaped first-name input without an application error. | Security | High | Medium | 200% | 200% | Automated | Pass | Y | N |  | Security payload probes are opt-in on shared demo; Headed desktop acceptance 07/10/2026.
TC-REG-018 | Registration | Handle XSS-shaped first-name input without script execution. | Security | High | Medium | 2 | 2 | Automated | Pass | Y | N |  | Security payload probes are opt-in on shared demo; Headed desktop acceptance 07/10/2026.
TC-SES-001 | Session | After logout, browser Back must not expose the authenticated overview. | Session | High | Medium | 200% | 200% | Automated | Pass | Y | N |  | Checks authenticated content is hidden; Headed desktop acceptance 07/10/2026.
TC-SES-002 | Session | Direct navigation to overview after logout returns the user to login. | Session | High | Medium | 2 | 2 | Automated | Pass | Y | N |  | Checks login view and absence of account data; Headed desktop acceptance 07/10/2026.
TC-ACC-001 | Accounts | Newly registered customer has a default account in the Accounts API. | API | High | Low | 300% | 300% | Automated | Pass | Y | N |  | API-seeded customer; Headed desktop acceptance 07/10/2026.
TC-ACC-002 | Accounts | Open a CHECKING account and verify its account ID and type through the API. | Functional | High | Medium | 3 | 3 | Automated | Pass | Y | N |  | API-funded source account; Headed desktop acceptance 07/10/2026.
TC-ACC-003 | Accounts | Open a SAVINGS account and verify its account ID and type through the API. | Functional | High | Medium | 300% | 300% | Automated | Pass | Y | N |  | API-funded source account; Headed desktop acceptance 07/10/2026.
TC-ACC-004 | Accounts | Reject account opening when the funding account has insufficient funds. | Negative | High | Medium | 3 | 3 | Automated | Fail | Y | N |  | Expected application gap: ParaBank opens an account from a zero-balance source. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-ACC-005 | Accounts | Open five accounts sequentially and reconcile account inventory and total balance. | E2E | High | High | 300% | 300% | Automated | Pass | Y | N |  | Multi-step flagship journey; Headed desktop acceptance 07/10/2026.
TC-ACC-006 | Accounts | Verify Accounts Overview account ID and balance against the Accounts API. | API/UI parity | High | Medium | 3 | 3 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-007 | Accounts | Verify one API-created account is listed in Accounts Overview. | Functional | Medium | Low | 300% | 300% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-008 | Accounts | Verify two API-created accounts are listed in Accounts Overview. | Functional | Medium | Low | 3 | 3 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-009 | Accounts | Verify three API-created accounts are listed in Accounts Overview. | Functional | Medium | Low | 300% | 300% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-010 | Accounts | Verify four API-created accounts are listed in Accounts Overview. | Functional | Medium | Low | 3 | 3 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-011 | Accounts | Verify five API-created accounts are listed in Accounts Overview. | Functional | Medium | Medium | 300% | 300% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-012 | Accounts | Create a CHECKING account through the API and verify the returned ID. | API | Medium | Low | 3 | 3 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-013 | Accounts | Create a SAVINGS account through the API and verify the returned ID. | API | Medium | Low | 300% | 300% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-014 | Accounts | Verify account balances are finite values with penny precision. | Data validation | Medium | Low | 3 | 3 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-ACC-015 | Accounts | Retrieve transaction history for a customer account through the API. | API | Medium | Low | 300% | 300% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-001 | Transfers | Transfer between own accounts and reconcile source debit and destination credit. | Functional | High | Medium | 4 | 4 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-002 | Transfers | Transfer the full available source balance and verify it reaches zero. | Boundary | High | Medium | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-003 | Transfers | Reject a transfer amount greater than the available balance. | Negative | High | Medium | 4 | 4 | Automated | Fail | Y | N |  | Expected application gap: ParaBank reports a successful transfer above the available balance. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-004 | Transfers | Reject a negative transfer amount. | Negative | High | Low | 400% | 400% | Automated | Fail | Y | N |  | Expected application gap: ParaBank accepts a negative transfer amount. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-005 | Transfers | Reject a zero transfer amount. | Boundary | High | Low | 4 | 4 | Automated | Fail | Y | N |  | Expected application gap: ParaBank accepts a zero transfer amount. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-006 | Transfers | Reject a non-numeric transfer amount. | Negative | High | Low | 400% | 400% | Automated | Fail | Y | N |  | Expected application gap: ParaBank reports a successful non-numeric transfer. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-007 | Transfers | Reject a transfer amount with more than two decimal places. | Boundary | Medium | Low | 4 | 4 | Automated | Fail | Y | N |  | Expected application gap: ParaBank accepts transfer amounts with more than two decimal places. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-008 | Transfers | Reject a transfer from an account to itself. | Negative | High | Medium | 400% | 400% | Automated | Fail | Y | N |  | Expected application gap: ParaBank reports a successful same-account transfer. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TRF-009 | Transfers | Perform ten rapid transfers and reconcile balances and debit/credit ledger counts. | E2E | High | High | 4 | 4 | Automated | Pass | Y | N |  | Multi-step flagship journey; Headed desktop acceptance 07/10/2026.
TC-TRF-010 | Transfers | Accept a transfer of the minimum positive currency value, 0.01. | Boundary | Medium | Low | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-011 | Transfers | Accept a whole-dollar transfer amount. | Functional | Medium | Low | 4 | 4 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-012 | Transfers | Accept a transfer amount with one decimal place. | Functional | Medium | Low | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-013 | Transfers | Accept a transfer amount with two decimal places. | Functional | Medium | Low | 4 | 4 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-014 | Transfers | Accept a 25.00 transfer when the source has sufficient funds. | Functional | Medium | Low | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-015 | Transfers | Transfer from a CHECKING account to a SAVINGS account. | Functional | Medium | Medium | 4 | 4 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-016 | Transfers | Transfer from a SAVINGS account to a CHECKING account. | Functional | Medium | Medium | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-017 | Transfers | Transfer between two CHECKING accounts. | Functional | Medium | Medium | 4 | 4 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TRF-018 | Transfers | API rejects a transfer to an unknown destination account. | API negative | High | Medium | 400% | 400% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-001 | Bill Pay | Pay a biller and verify confirmation and matching source-account debit. | E2E | High | Medium | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-002 | Bill Pay | Reject bill payment when payee name is blank. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-003 | Bill Pay | Reject bill payment when payee street address is blank. | Negative | High | Low | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-004 | Bill Pay | Reject bill payment when payee city is blank. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-005 | Bill Pay | Reject bill payment when payee state is blank. | Negative | High | Low | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-006 | Bill Pay | Reject bill payment when payee ZIP/postcode is blank. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-007 | Bill Pay | Reject bill payment when payee phone number is blank. | Negative | High | Low | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-008 | Bill Pay | Reject bill payment when payee account number is blank. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-009 | Bill Pay | Reject bill payment when account-number confirmation is blank. | Negative | High | Low | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-010 | Bill Pay | Reject bill payment when amount is blank. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-011 | Bill Pay | Reject bill payment when account and verification account numbers do not match. | Negative | High | Medium | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-012 | Bill Pay | Accept bill payment for the minimum positive amount, 0.01. | Boundary | Medium | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-013 | Bill Pay | Reject a zero-amount bill payment. | Boundary | High | Low | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-014 | Bill Pay | Reject a bill payment with a blank amount. | Negative | High | Low | 500% | 500% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-015 | Bill Pay | Reject a negative bill payment amount. | Negative | High | Low | 5 | 5 | Automated | Fail | Y | N |  | Expected application gap: ParaBank accepts negative bill payments and mutates the balance. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-BPY-016 | Bill Pay | Reject bill payment exceeding the available balance. | Negative | High | Medium | 500% | 500% | Automated | Fail | Y | N |  | Expected application gap: ParaBank permits bill payments that overdraw the source account. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-BPY-017 | Bill Pay | Pay the same biller twice and verify two separate debits. | Functional | High | Medium | 5 | 5 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-BPY-018 | Bill Pay | Pay ten billers from JSON data and reconcile total debits and transactions. | E2E | High | High | 500% | 500% | Automated | Pass | Y | N |  | Multi-step flagship journey; Headed desktop acceptance 07/10/2026.
TC-TXN-001 | Transactions | Find a transaction by transaction ID. | Positive | High | Low | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-002 | Transactions | Find transactions by transaction date. | Positive | High | Low | 600% | 600% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-003 | Transactions | Find transactions within an inclusive date range. | Positive | High | Medium | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-004 | Transactions | Find a transaction by exact amount. | Positive | High | Low | 600% | 600% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-005 | Transactions | Handle a date range whose start and end dates are equal. | Boundary | Medium | Low | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-006 | Transactions | Handle a date range whose end date is earlier than its start date. | Negative | High | Low | 600% | 600% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-007 | Transactions | Handle an invalid date format in a date-range search. | Negative | High | Low | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-008 | Transactions | Handle a future date in a date-range search. | Boundary | Medium | Low | 600% | 600% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-009 | Transactions | Show an empty state when amount search has no matching transaction. | Negative | Medium | Low | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-010 | Transactions | Seed 55 transactions and find the newest transaction through UI search. | Volume | High | High | 600% | 600% | Automated | Pass | Y | N |  | API-only high-volume setup; Headed desktop acceptance 07/10/2026.
TC-TXN-011 | Transactions | Show the seeded transaction volume in account activity without losing rows. | Volume | High | High | 6 | 6 | Automated | Pass | Y | N |  | API-only high-volume setup; Headed desktop acceptance 07/10/2026.
TC-TXN-012 | Transactions | List the newest seeded transaction first in high-volume account activity. | Volume | High | High | 600% | 600% | Automated | Fail | Y | N |  | Expected application gap: ParaBank account activity is ordered oldest-first, not newest-first. Reproduced in the isolated headed run; this is not an unexpected automation failure.
TC-TXN-013 | Transactions | Reconcile account activity against the API for funded account 1. | Reconciliation | High | Medium | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-014 | Transactions | Reconcile account activity against the API for funded account 2. | Reconciliation | High | Medium | 600% | 600% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-TXN-015 | Transactions | Reconcile account activity against the API for funded account 3. | Reconciliation | High | Medium | 6 | 6 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-001 | Lending | Approve a valid loan and show the new loan account in overview. | Positive | High | High | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-002 | Lending | Deny a loan when down payment exceeds available source funds. | Negative | High | Medium | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-003 | Lending | Handle a loan application with zero loan amount. | Boundary | High | Low | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-004 | Lending | Handle a loan application with negative loan amount. | Negative | High | Low | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-005 | Lending | Handle a loan application with blank down payment. | Negative | High | Low | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-006 | Lending | Handle a loan application with non-numeric down payment. | Negative | High | Low | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-007 | Lending | Handle a down payment equal to the loan amount. | Boundary | Medium | Medium | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-008 | Lending | Check loan approval-matrix combination 1. | Decision matrix | High | Medium | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-009 | Lending | Check loan approval-matrix combination 2. | Decision matrix | High | Medium | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-010 | Lending | Check loan approval-matrix combination 3. | Decision matrix | High | Medium | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-011 | Lending | Check loan approval-matrix combination 4. | Decision matrix | High | Medium | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-012 | Lending | Check loan approval-matrix combination 5. | Decision matrix | High | Medium | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-013 | Lending | Transfer funds out of an approved loan account. | Functional | High | Medium | 700% | 700% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-014 | Lending | Show the approved loan account in Accounts Overview. | Functional | High | Medium | 7 | 7 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-LND-015 | Lending | Register, fund savings, obtain an approved loan, pay a bill, and reconcile the complete ledger. | E2E | High | High | 700% | 700% | Automated | Pass | Y | N |  | Flagship journey; Headed desktop acceptance 07/10/2026.
TC-API-001 | API | Create and retrieve a customer through the REST customer resource. | Positive | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-002 | API | Retrieve the registered customer's seed-account collection. | Positive | High | Low | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-003 | API | Open a checking account through the REST API. | Positive | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-004 | API | Open a savings account through the REST API. | Positive | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-005 | API | Retrieve account details through the REST API. | Positive | High | Low | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-006 | API | Deposit funds and find the resulting transaction. | Positive | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-007 | API | Retrieve transaction identifiers and amounts. | Positive | High | Low | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-008 | API | Transfer funds and verify source debit and destination credit. | Positive | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-009 | API | Pay a bill and verify the debit and recorded transaction. | Positive | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-010 | API | Return no customer record for an unknown customer ID. | Negative | High | Low | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-011 | API | Return no account record for an unknown account ID. | Negative | High | Low | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-012 | API | Return no transaction record for an unknown account ID. | Negative | High | Low | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-013 | API | Reject a transfer with missing required parameters. | Negative | High | Low | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-014 | API | Reject a bill payment with missing required parameters. | Negative | High | Low | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-015 | API | Reject JSON transfer content without mutating either account balance. | Negative | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-016 | API | Validate required customer fields in the REST XML response. | Contract | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-017 | API | Validate account fields and balance in the REST XML response. | Contract | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-018 | API | Validate transaction fields in the REST XML response. | Contract | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-019 | API | Match SOAP customer lookup with the REST customer record. | Parity | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-020 | API | Match SOAP account lookup with the REST account record. | Parity | High | Medium | 800% | 800% | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-021 | API | Verify SOAP transaction lookup returns REST transaction identifiers. | Parity | High | Medium | 8 | 8 | Automated | Pass | Y | N |  | API-only; Headed desktop acceptance 07/10/2026.
TC-API-022 | API | Create customer, account, transfer, bill payment, and reconcile ledger using only APIs. | E2E | High | High | 800% | 800% | Automated | Pass | Y | N |  | API-only flagship; Headed desktop acceptance 07/10/2026.
TC-CHN-001 | Channels | Log in successfully in Chromium. | Cross-browser | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-002 | Channels | Display Accounts Overview in Chromium. | Cross-browser | High | Medium | 900% | 900% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-003 | Channels | Transfer between own accounts in Chromium. | Cross-browser | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-004 | Channels | Pay a bill in Chromium. | Cross-browser | High | Medium | 900% | 900% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-005 | Channels | Hide authenticated account links after logout in Chromium. | Cross-browser | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-006 | Channels | Keep keyboard focus in the expected order on the login form. | Accessibility | Medium | Low | 900% | 900% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-007 | Channels | Keep login form controls inside a 390×844 mobile viewport. | Responsive | Medium | Medium | 9 | 9 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-008 | Channels | Expose account and balance headings in the overview table. | Accessibility | Medium | Low | 900% | 900% | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-009 | Channels | Show every required payee field in the bill-pay form. | Functional | Medium | Low | 9 | 9 | Automated | Pass | Y | N |  | ; Headed desktop acceptance 07/10/2026.
TC-CHN-010 | Accessibility | Scan login page and attach axe violations for reporting. | Accessibility | High | Medium | 900% | 900% | Automated | Pass | Y | N |  | Violations are attached and summarized; accessibility findings are reported, not asserted away.; Headed desktop acceptance 07/10/2026. Axe violations attached and annotated; findings are reported rather than asserted away.
TC-CHN-011 | Accessibility | Scan overview page and attach axe violations for reporting. | Accessibility | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | Violations are attached and summarized; accessibility findings are reported, not asserted away.; Headed desktop acceptance 07/10/2026. Axe violations attached and annotated; findings are reported rather than asserted away.
TC-CHN-012 | Accessibility | Scan transfer page and attach axe violations for reporting. | Accessibility | High | Medium | 900% | 900% | Automated | Pass | Y | N |  | Violations are attached and summarized; accessibility findings are reported, not asserted away.; Headed desktop acceptance 07/10/2026. Axe violations attached and annotated; findings are reported rather than asserted away.
TC-CHN-013 | PayID Simulation | Handle a mocked settled PayID/NPP payment response. | Integration | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | Mock simulation; no native ParaBank PayID; Headed desktop acceptance 07/10/2026.
TC-CHN-014 | PayID Simulation | Handle a mocked failed PayID/NPP payment response. | Integration | High | Medium | 900% | 900% | Automated | Pass | Y | N |  | Mock simulation; no native ParaBank PayID; Headed desktop acceptance 07/10/2026.
TC-CHN-015 | PayID Simulation | Handle a mocked timeout PayID/NPP payment response. | Integration | High | Medium | 9 | 9 | Automated | Pass | Y | N |  | Mock simulation; no native ParaBank PayID; Headed desktop acceptance 07/10/2026.

## Productivity Dashboard
Productivity Dashboard |  | Productivity | Share
Auto-calculated from Daily Log and Test Case Tracker — no manual entry on this sheet. |  | Pass | 133
|  | Fail | 11
Overall Volume |  | Blocked | 0
Total test cases logged | 144 | Not Run | 0
Automated | 144 | Flaky | 0
In Progress | 0
Blocked | 0
Pass rate (Pass ÷ (Pass + Fail)) | 92.36%
Flakiness rate (Flaky ÷ Automated) | 0%
Quality
Pass | 133
Fail | 11
Flaky | 0
Not Run | 0
Pass rate (Pass ÷ (Pass + Fail)) | 92.36%
Flakiness rate (Flaky ÷ Automated) | 0%
By Priority
Critical | 0
High | 115
Medium | 29
Low | 0
By Complexity
Low | 71
Medium | 64
High | 9
Complexity-weighted volume (L×1 + M×2 + H×3) | 226
Velocity & Reliability
Average cases completed / day | 16
Total hours spent | 0
Cases per hour | Not tracked
Total flaky tests introduced | 0
Total flaky tests fixed | 0
Flaky tests remaining open | 0
Total defects logged | 1
Design & Reuse
Test cases using a reusable component | 144
Reuse rate (of Automated cases) | 100%

## Scorecard
Individual Productivity Scorecard
Evaluator fills the Rating column (1–5) at the end of Day 10. Everything else calculates.
Criterion | Weight | Rating (1-5) | Weighted Score | Comments
Velocity (cases completed vs. plan, complexity-adjusted) | 25% |  | 0
Quality / first-run pass rate | 20% |  | 0
Design & reuse (POM, data-driven, shared utilities) | 20% |  | 0
Flakiness discipline (introduced vs. fixed by Day 10) | 15% |  | 0
Complex end-to-end capability (chained flagship scenarios) | 15% |  | 0
Communication (daily logs, final report clarity) | 5% |  | 0
TOTAL | 100% |  | 0
Score out of 5 | 0
Overall Band | Needs Support
Calibration: Strong ≥ 4.00 ¦ Developing 2.50–3.99 ¦ Needs Support < 2.50

## Application Coverage
Application | Automation Suite | Platform / Profile | Planned Cases | Completed | Passed | Failed | Skipped / Blocked | Run Status | Run Date | Observed Result / Notes
ParaBank | Playwright (single worker) | Desktop Chromium | 77 | 73 | 60 | 13 | 4 | Completed with failures/skips | 28/09/2026 | Full run summary: 60 passed, 13 failed, 4 skipped. Public target had validation/server inconsistencies.
ParaBank | Playwright headed parallel | Desktop Chromium | 77 | 0 | 0 | 0 | 77 | Blocked before execution | 28/09/2026 | Preflight stopped the run because the shared public demo returned Cloudflare 1015; no cases executed.
ACME Demo | Playwright web suite (headed) | Desktop Chromium | 4 | 4 | 4 | 0 | 0 | Passed | 28/09/2026 | All four functional, accessibility, API and visual tests passed.
ACME Demo | Playwright web suite (headed) | Playwright iPhone 13 emulation | 4 | 4 | 4 | 0 | 0 | Passed | 28/09/2026 | All four functional, accessibility, API and visual tests passed.
ACME Demo | Playwright web suite (headed) | Playwright Pixel 5 emulation | 4 | 4 | 3 | 1 | 0 | Completed with one failure | 28/09/2026 | Functional, accessibility and API tests passed; dashboard visual snapshot failed.
ACME Demo | Playwright web suite (headed) | Playwright Galaxy S9+ emulation | 4 | 4 | 4 | 0 | 0 | Passed | 28/09/2026 | All four functional, accessibility, API and visual tests passed.
ACME Demo | Playwright web suite (headed) | Playwright iPhone 12 emulation | 4 | 4 | 4 | 0 | 0 | Passed | 28/09/2026 | All four functional, accessibility, API and visual tests passed.
ACME Demo | Playwright web suite (headed) | Playwright Pixel 7 emulation | 4 | 4 | 4 | 0 | 0 | Passed | 28/09/2026 | All four functional, accessibility, API and visual tests passed.
ACME Demo | Playwright web suite total | Six projects / viewport profiles | 24 | 24 | 23 | 1 | 0 | Completed with one failure | 28/09/2026 | Latest headed run: 23 passed, 1 failed.
ACME Demo | WebdriverIO + Appium | Android Chrome ? Pixel_10_Pro_Fold (emulator-5554) | 1 | 0 | 0 | 0 | 1 | Blocked | 28/09/2026 | Session creation failed; configured Android device was not connected/visible to Appium.
ACME Demo | WebdriverIO + Appium | Android Chrome ? Pixel_10_Pro (emulator-5556) | 1 | 0 | 0 | 0 | 1 | Blocked | 28/09/2026 | Session creation failed; configured Android device was not connected/visible to Appium.
ACME Demo | WebdriverIO + Appium | Android Chrome ? Pixel_6 (emulator-5558) | 1 | 0 | 0 | 0 | 1 | Blocked | 28/09/2026 | Session creation failed; configured Android device was not connected/visible to Appium.
ACME Demo | WebdriverIO + Appium total | Three configured Android emulators | 3 | 0 | 0 | 0 | 3 | Blocked | 28/09/2026 | No test reached the application; all device sessions were blocked by device availability.
ACME Demo | Cucumber mobile BDD | Android Chrome ? Pixel_10_Pro_Fold (emulator-5554) | 1 | 0 | 0 | 0 | 0 | Not Run |  | Mobile BDD command was not reached in the recorded run.
ACME Demo | Cucumber mobile BDD | Android Chrome ? Pixel_10_Pro (emulator-5556) | 1 | 0 | 0 | 0 | 0 | Not Run |  | Mobile BDD command was not reached in the recorded run.
ACME Demo | Cucumber mobile BDD | Android Chrome ? Pixel_6 (emulator-5558) | 1 | 0 | 0 | 0 | 0 | Not Run |  | Mobile BDD command was not reached in the recorded run.
ACME Demo | Cucumber mobile BDD total | Three configured Android emulators | 3 | 0 | 0 | 0 | 0 | Not Run |  | No mobile BDD result is claimed.
ParaBank | ParaBank Android/platform matrix | Mobile viewport / Android matrix | 77 | 0 | 0 | 0 | 0 | Not Run |  | Matrix runner is configured but was not executed in this session.
ParaBank | Playwright (single worker rerun) | Desktop Chromium | 77 | 73 | 27 | 46 | 4 | Completed with rate-limit errors | 28/09/2026 | Later serial rerun summary: 27 passed, 46 failed, 4 skipped; shared public demo responses included HTTP 429/Cloudflare 1015. Treat these results as environment-limited.
ParaBank | Playwright headed full acceptance | Desktop Chromium | 14400% | 14400% | 13300% | 1100% | 0% | Completed; expected product gaps | 07/10/2026 | Isolated target. 11 known application validation/ordering gaps; zero unexpected automation failures.
ParaBank | Day 9 cross-channel suite | Headed Chromium | 1500% | 1500% | 1500% | 0% | 0% | Passed | 07/10/2026 | All 15 channel, responsive, accessibility-reporting and mocked PayID cases passed.
ParaBank | Day 9 cross-channel suite | Headed Firefox | 1500% | 1500% | 1500% | 0% | 0% | Passed | 07/10/2026 | 15/15 passed in isolated headed Firefox run.
ParaBank | Day 9 cross-channel suite | Headed mobile viewport 390x844 | 1500% | 1500% | 1500% | 0% | 0% | Passed | 07/10/2026 | 15/15 passed.
ParaBank | REST/SOAP API suite | API only (no browser) | 2200% | 2200% | 2200% | 0% | 0% | Passed | 07/10/2026 | 22/22 passed; REST, SOAP parity and API E2E.
ParaBank | Gherkin feature | Headed Chromium | 400% | 400% | 400% | 0% | 0% | Passed | 07/10/2026 | 4 scenarios and 29 steps passed.
ParaBank | Day 10 three-run stability | Desktop Chromium | 43200% | 43200% | 39900% | 3300% | 0% | Passed; zero flaky | 07/10/2026 | Three x 144 tests. 33 expected application gaps; zero unexpected, skipped or flaky.